## StartHere
QE learning workbook | Planning examples, not executed results
Target | Local DotNet10/10-Capstone API: integer IDs; raw title limit 200 UTF-16 units
Start | Read QualityEngineering/README.md and Workbook-Guide.md
WorstCases | Rank harm, clarify scope, choose the next experiment
TestCases | 16 planned cases; use actual lab evidence when updating your own copy
Defects | TRAINING-01 is fictional and has no observation evidence
Coverage | Links express planned coverage, not passing execution
Lifecycle | Track QE deliverables from discovery through operation
Risk formula | Likelihood x impact; High >=15, Medium 8-14, Low 1-7; impact 5 always High
Status | Not run = no evidence; Failed = observed mismatch; Blocked = unable to execute
Important | Scores are estimates. A colored cell is not evidence of a defect.
Execution reports | Run Labs/Invoke-ApiChecks.ps1; inspect its unique .artifacts/qe-run-* report
Regenerate | Build-Workbook.ps1 overwrites this workbook from CSVs; preserve personal notes separately
Risk matrix: impact vs likelihood
Impact / Likelihood | 1 | 2 | 3 | 4 | 5
5 | 5 | 10 | 15 | 20 | 25
4 | 4 | 8 | 12 | 16 | 20
3 | 3 | 6 | 9 | 12 | 15
2 | 2 | 4 | 6 | 8 | 10
1 | 1 | 2 | 3 | 4 | 5

## WorstCases
RiskId | Feature | Failure | Trigger | Impact | Likelihood | ImpactScore | Score | Priority | ExpectedProtection | Approach | Status | Scope | Owner
RK-01 | Persistence | Saved task missing after restart | Restart with same data path | Loss of trusted study records | 3 | 5 | 15 | High | Same-path restart preserves identity and state | Run TC-11; compare response and stored file | Not run | Local API | Learner
RK-02 | Saving | Success reported after failed save | Controlled storage failure | User believes missing data is safe | 2 | 5 | 10 | High | Failure is visible; previous valid state checked | Use isolated failing adapter/path; inspect response and state | Not run | Local API | Learner
RK-03 | Validation | Overlong title accepted | Raw title length 201 | Stored state violates agreed rule | 3 | 3 | 9 | Medium | 400 and no extra task | Boundary TC-05 and TC-06 | Not run | Local API | Learner
RK-04 | Validation | Blank or missing title stored | Whitespace or absent field | Unusable task enters data | 3 | 3 | 9 | Medium | 400 and unchanged collection | TC-04 and TC-15 | Not run | Local API | Learner
RK-05 | Identity | Unknown ID changes another task | Absent integer ID | Incorrect item modified | 2 | 4 | 8 | Medium | 404; existing state unchanged | Absent ID plus compare state | Not run | Local API | Learner
RK-06 | Completion | Repeated completion duplicates task | Complete same ID twice | Inconsistent task state | 2 | 4 | 8 | Medium | Same identity; one completed record | TC-09 and TC-10 | Not run | Local API | Learner
RK-07 | Input binding | Malformed body changes data | Broken JSON or wrong title type | Invalid request has side effects | 3 | 4 | 12 | Medium | 400; no added task | TC-07 and TC-16 | Not run | Local API | Learner
RK-08 | Deletion | Wrong task removed | Delete an existing ID among several | Severe loss of unrelated data | 2 | 5 | 10 | High | Only selected task disappears | TC-12/13/14; inspect other task | Not run | Local API | Learner
RK-09 | Recovery | Corrupt storage silently treated as empty | Start with corrupt disposable JSON | Loss hidden by apparently healthy app | 2 | 5 | 10 | High | Visible startup/read failure; preserve evidence | Manual controlled corrupt-data startup | Not run | Local API | Learner
RK-10 | Concurrency | Updates lost in one server process | Overlapping valid requests | One accepted update disappears | 3 | 4 | 12 | Medium | All successful distinct updates remain | Design controlled overlap test; compare IDs | Not run | Local API | Learner
RK-11 | Deployment | Independent writers overwrite data | Two servers share one file | Severe data loss | 2 | 5 | 10 | High | Restrict deployment or redesign persistence | Architecture review; do not assume in-process lock coordinates servers | Known limitation | Outside current deployment | Learner
RK-12 | Configuration | App appears to lose tasks | Restart with different data path | Confusing apparent loss | 3 | 4 | 12 | Medium | Path/configuration is understood and verified | Compare process arguments and paths | Not run | Local API | Learner
RK-13 | Data integrity | Invalid stored records accepted | Malformed semantic data in valid JSON | Incorrect identity or task state | 2 | 4 | 8 | Medium | Invalid state rejected visibly | Controlled copied-data cases; inspect startup log | Not run | Local API | Learner
RK-14 | Performance | Response unacceptably slow | Agreed large dataset and request load | Learning workflow blocked | 3 | 3 | 9 | Medium | Meets an agreed measured target | Define load and target before measuring | Needs requirement | Local API | Learner
RK-15 | Ownership | One user reads another user's task | Proposed shared service | Sensitive data disclosed | 3 | 5 | 15 | High | Agreed ownership and access control | Define identities; test authorization in future design | Needs requirement | Proposed shared service | Product owner
RK-16 | Accessibility | User cannot complete a task | Proposed UI with keyboard/assistive tech | User excluded from core workflow | 3 | 4 | 12 | Medium | Usable accessible interaction | Keyboard and accessibility review of future UI | Needs requirement | Proposed browser UI | Product owner
RK-17 | Retry | One user action creates duplicates | Proposed client times out and retries | Confusing duplicate work | 3 | 4 | 12 | Medium | Agreed logical-submission behavior | Investigate commit timing and retry policy | Needs requirement | Proposed networked client | Product owner
RK-18 | Recovery | Backup cannot restore valid tasks | Restore after a failure | Severe data loss | 2 | 5 | 10 | High | Documented tested restoration | Restore a copy; verify IDs and completion state | Not run | Local API | Learner

## TestCases
CaseId | RequirementId | RiskId | Title | Preconditions | Input | Steps | ExpectedResult | Level | Technique | Status | ActualResult | Evidence
TC-01 | R-00 |  | Ready server responds | Isolated server started | GET /health | Send request | 200; status=ok | API | Smoke | Not run
TC-02 | R-02 |  | Empty store lists no tasks | Fresh isolated data | GET /tasks | Read collection | 200; empty array | API | State | Not run
TC-03 | R-01 | RK-01 | Valid task is created | Empty store | title=" QE task " | POST then inspect record | 201; positive ID; trimmed title; incomplete | API | Happy path | Not run
TC-04 | R-03 | RK-04 | Blank title rejected | One existing task | title=" " | POST then read count | 400; count still 1 | API | Partition | Not run
TC-05 | R-03 | RK-03 | Maximum raw length accepted | One existing task | 200 ASCII characters | POST then inspect record | 201; exact title; count 2 | API | Boundary | Not run
TC-06 | R-03 | RK-03 | Above maximum rejected | Two existing tasks | 201 ASCII characters | POST then read count | 400; count still 2 | API | Boundary | Not run
TC-07 | R-03 | RK-07 | Malformed JSON rejected | Two existing tasks | { broken | POST raw body; read count | 400; count still 2 | API | Invalid format | Not run
TC-08 | R-02 | RK-05 | Missing ID not found | Known IDs are small positive values | GET /tasks/2147483647 | Read absent item | 404; collection unchanged | API | Missing state | Not run
TC-09 | R-04 | RK-06 | Complete task preserves identity | TC-03 task exists | PUT /tasks/{createdId}/complete | Complete then inspect | 200; same ID/title; isComplete=true | API | Transition | Not run
TC-10 | R-04 | RK-06 | Complete again creates no duplicate | TC-09 completed task | Same PUT again | Complete; inspect count | 200; same task completed; count 2 | API | Repeated action | Not run
TC-11 | R-06 | RK-01 | Restart preserves saved state | Completed task and boundary task saved | Restart using same file | Stop owned process; start new process; GET task | 200; original ID/title; completed; count 2 | Integration | Persistence | Not run
TC-12 | R-05 | RK-08 | Delete removes only target | Two saved tasks | DELETE /tasks/{createdId} | Delete; read collection | 204; only boundary task remains | API | Transition | Not run
TC-13 | R-05 | RK-08 | Deleted task cannot be read | TC-12 removed task | GET /tasks/{createdId} | Read deleted item | 404; boundary task remains | API | Deleted state | Not run
TC-14 | R-05 | RK-08 | Repeated delete reports missing | TC-12 removed task | DELETE same ID | Delete again; read count | 404; count still 1 | API | Repeated action | Not run
TC-15 | R-03 | RK-04 | Missing title rejected | One boundary task remains | {} | POST then read count | 400; count still 1 | API | Missing input | Not run
TC-16 | R-03 | RK-07 | Wrong title type rejected | One boundary task remains | {"title":123} | POST then read count | 400; count still 1 | API | Invalid type | Not run

## Defects
BugId | Title | Scope | Status | Severity | Priority | Expected | Actual | Evidence | Hypothesis | NextAction
TRAINING-01 | Possible duplicate after timeout and retry | Fictional proposed networked client | Training example | Unassessed | Unassessed | Needs agreed logical-submission contract | Fictional: two IDs after one reported client action | None - not observed | First request may have committed before response loss | Clarify requirement; capture request/response timeline

## Coverage
RequirementId | Behavior | RiskIds | PlannedCaseIds | AutomatedEvidence | RemainingGap | Owner
R-00 | Readiness |  | TC-01 | Lab report after execution | No availability/SLA measurement | Learner
R-01 | Create a valid task | RK-01 | TC-03 | Lab report after execution | Other Unicode/normalization partitions | Learner
R-02 | Read collection/item | RK-05 | TC-02;TC-08 | Lab report after execution | Malformed route variants and large collections | Learner
R-03 | Reject invalid titles/bodies | RK-03;RK-04;RK-07 | TC-04;TC-05;TC-06;TC-07;TC-15;TC-16 | Lab report after execution | Raw padding and Unicode boundaries remain manual | Learner
R-04 | Complete and repeat | RK-06 | TC-09;TC-10 | Lab report after execution | Absent completion and overlap checks remain | Learner
R-05 | Delete and repeat | RK-08 | TC-12;TC-13;TC-14 | Lab report after execution | Concurrent delete/read behavior | Learner
R-06 | Same-file restart persistence | RK-01;RK-09;RK-18 | TC-11 | Lab report after execution | Crash durability and backup restore untested | Learner
R-07 | Visible storage failure | RK-02;RK-13 |  | No automated case in this lab | Controlled write failure and state consistency | Learner
R-08 | Local deployment scope | RK-11;RK-15;RK-16;RK-17 |  | Review scope and assumptions | No shared identity model or browser UI | Product owner

## Lifecycle
Stage | QEQuestion | Artifact | VisualTool | Owner | Status | Evidence
Discovery | Who could be harmed? | User journey and question list | Paper / draw.io | Learner | Not started
Requirements | How will we observe correctness? | Acceptance table | Workbook / editor | Learner | Not started
Design | Where can failures cross boundaries? | State and sequence model | draw.io | Learner | Not started
Planning | What should we learn first? | Risk register and coverage | Workbook | Learner | Not started
Development | Which small check gives early feedback? | Component evidence | IDE / terminal | Learner | Not started
Integration | Do contracts and persisted state agree? | API results | Postman / local HTML report | Learner | Not started
Exploration | What did we not anticipate? | Charter and notes | Notebook / diagram | Learner | Not started
Fixing | What explains and prevents the failure? | Bug report and retest | Issue board / IDE | Learner | Not started
Release | Which risks remain? | Test summary and recommendation | Workbook / report | Decision owner | Not started
Operation | What should change after real feedback? | Incident learning | Timeline / issue board | Team | Not started